## 📋 Executive Summary
GRADMATCH — AI-POWERED GRADUATE SCHOOL MATCHING SYSTEM
14-Week Project Plan · Jan 26, 2026 → May 03, 2026 · Proposal April 2026
🎓 PROJECT BRIEF
🎯 | Problem Statement | Graduate school search is fragmented and overwhelming: 20,000+ programs worldwide, 4,000+ in the US alone. No centralized intelligent matching platform exists. Students rely on peer advice and generic searches, leading to poor program fit and elevated attrition rates.
💡 | Solution: GradMatch | An AI-powered platform combining Machine Learning (GNN, BERT, NCF), NLP semantic matching, and Collaborative Filtering to connect the right student to the right graduate program — with Explainable AI so students understand every recommendation.
🏛️ | Academic Context | Mixed-methods research project using Agile-iterative methodology. Integrates systematic literature review, stakeholder interviews (30 students + 10 institutions), quantitative ML evaluation, and usability testing to validate all design decisions.
🌍 | Target Users | Primary: Prospective graduate students (domestic & international, incl. first-gen). Secondary: University admissions officers, program coordinators, and faculty. Tertiary: Academic advisors and research mentors.
🔬 | Research Gaps Addressed | 1) Longitudinal outcome tracking (5-year cohort data vs click-through metrics). 2) Bilateral institutional design (two-sided matching). 3) System-level diversity impact measurement. 4) Fairness-aware ML in graduate admissions context.
⚖️ | Ethics & Compliance | FERPA & GDPR compliant by design. WCAG 2.1 AA accessibility. Fairness-aware ML with adversarial debiasing. Demographic parity auditing. Diversity-promotion in recommendation objective. No opaque composite scores — full Explainable AI.
📐 PHASE ROADMAP
| Phase | Focus | Weeks | Start | End
🔵 | Phase 1 – Requirements & Research | Systematic literature review (50+ papers) · 30 student interviews · 10 institution focus groups · Competitive analysis (GradCafe, Naviance, UniMatch AI) · Research questions finalization · IRB/ethics approval | Wk 1–2 | Jan 26, 2026 | Feb 08, 2026
🟣 | Phase 2 – System & ML Design | 5-layer architecture design (Presentation→App→Service→Data→Infra) · ML pipeline: GNN + BERT/SciBERT + NCF + Matrix Factorization · Database schema (PostgreSQL + Redis + Document Store) · OpenAPI 3.0 spec · Figma UX wireframes · Fairness framework · FERPA/GDPR architecture | Wk 3–5 | Feb 09, 2026 | Mar 01, 2026
🟠 | Phase 3 – Agile Development (4 Sprints) | Sprint 1: Auth, profiles, CI/CD · Sprint 2: ML matching engine (collaborative filtering, BERT embeddings) · Sprint 3: GNN layer, Explainable AI (SHAP/LIME), student web app · Sprint 4: University admin portal, analytics dashboard, notification engine, mobile app beta | Wk 6–9 | Mar 02, 2026 | Mar 29, 2026
🟢 | Phase 4 – Testing & Validation | Unit + integration testing (≥80% coverage) · ML evaluation: Precision@10, AUC ≥0.87 · Algorithmic fairness audit across demographic groups · Usability think-alouds (SUS ≥4.0/5.0) · WCAG 2.1 AA audit · FERPA/GDPR compliance sign-off · Performance & load testing | Wk 10–12 | Mar 30, 2026 | Apr 19, 2026
🔴 | Phase 5 – Pilot Deployment | Deploy to 3 partner institutions · Admin onboarding sessions · Pre/post student surveys · 5-year cohort tracking framework setup · Real-time performance monitoring · Stakeholder feedback synthesis · Phase 6 planning: federated learning, RL optimization, LLM personal statement coaching | Wk 13–14 | Apr 20, 2026 | May 03, 2026

## 📅 Weekly Detailed Tasks
GRADMATCH — DETAILED WEEKLY TASK BREAKDOWN
Jan 26, 2026 → May 03, 2026 · Status auto-calculated as of May 04, 2026
Week | Task / Milestone | Start Date | End Date | Detailed Activities | Deliverables & Outputs | Status | Phase | Owner
Wk 1 | Wk 1 – Project Kick-off & Team Setup | 2026-01-26 | 2026-02-01 | • Form core team (PM, Research Lead, Tech Lead, ML Lead, UX Lead, QA, DevOps, Legal) • Define RACI matrix and communication protocols • Set up GitHub monorepo, Jira board, Confluence wiki • Establish coding standards, branching strategy (GitFlow) • Draft and submit IRB/ethics application for human subjects research • Initial competitive landscape mapping: GradCafe, Naviance, UniMatch AI • Schedule all 30 student + 10 institution interview slots | Project charter · RACI matrix · GitHub repo initialized · Jira epic/story structure · Confluence home page · IRB application submitted · Interview schedule confirmed · Team onboarding checklist ✓ | ✅ Complete | Phase 1 | Project Manager
Wk 2 | Wk 2 – Stakeholder Research & Literature Review | Feb 02, 2026 | Feb 08, 2026 | • Conduct 30 semi-structured student interviews (research interests, GPA, program search pain points, advising access equity) • Run 10 institution focus groups (admissions criteria, program culture, data sharing willingness) • Systematic literature review: ML-based recommender systems, graduate education outcomes, fairness in AI, NLP for academic matching • Analyze existing platforms: GradCafe (community Q&A, no ML), Naviance (K-12 focus, partial matching), UniMatch AI (ML but no admin portal/open API) • Identify research gaps: longitudinal outcomes, bilateral design, diversity impact | 30 interview transcripts (NVivo coded) · 10 focus group summaries · Literature review matrix (50+ papers) · Competitive analysis matrix (6 features × 4 platforms) · Research gap report · Persona drafts (5 student archetypes + 3 institution types) | ✅ Complete | Phase 1 | Research Lead
Wk 3 | Wk 3 – Requirements Elicitation & Scoping | Feb 09, 2026 | Feb 15, 2026 | • Synthesize interview findings into functional requirements • Define non-functional requirements: FERPA/GDPR compliance, WCAG 2.1 AA, 99.5% uptime, <2s API response time, mobile-first • Build full user story backlog (100+ stories) with MoSCoW prioritization • Create use case diagrams: student profile → matching → application tracking → notifications; institution portal → applicant review → analytics • Define data dictionary v1: student fields (GPA, GRE, research interests, publications), program fields (ranking, faculty research areas, funding), interaction events • Agree on MVP feature scope vs. future phases | Functional requirements doc (v1.0) · Non-functional requirements doc · Use case diagrams (UML) · User story backlog in Jira (100+ stories, MoSCoW tagged) · Data dictionary v1 · MVP scope agreement · Stakeholder sign-off | ✅ Complete | Phase 2 | BA / Research Lead
Wk 4 | Wk 4 – System Architecture & Database Design | Feb 16, 2026 | Feb 22, 2026 | • Design 5-layer architecture: L1 Presentation: React web + React Native mobile L2 Application: Django/FastAPI business logic, session state L3 Service: ML Engine, Recommender Service, Analytics Pipeline, Notification Engine L4 Data: PostgreSQL (relational), MongoDB (document store), Redis (cache) L5 Infrastructure: AWS ECS (containers), ALB, CloudWatch, S3 • Design ER diagram: Users, StudentProfiles, Programs, Applications, Recommendations, Interactions, FacultyProfiles • Write OpenAPI 3.0 specification for all endpoints • Design FERPA/GDPR data architecture: purpose limitation, data minimization, encryption at rest/transit • Set up AWS dev environment, VPC, IAM roles | Architecture document (5-layer diagram) · ER diagram (PostgreSQL schema) · OpenAPI 3.0 spec (all endpoints) · AWS infrastructure blueprint (VPC, ECS, RDS, ElastiCache) · Data privacy architecture doc · Security model (OAuth 2.0, JWT, AES-256 encryption) · Tech stack decision log | ✅ Complete | Phase 2 | Tech Lead / Architect
Wk 5 | Wk 5 – ML Pipeline Design & UX Wireframes | Feb 23, 2026 | Mar 01, 2026 | • Design full ML matching pipeline: — Collaborative Filtering: Matrix Factorization (SVD), Neural Collaborative Filtering (NCF) — Graph Neural Networks: model student-program-faculty interaction graph — NLP: BERT/SciBERT embeddings for research interest semantic similarity, TF-IDF + Word Vectors fallback — Admissions Prediction: Gradient Boosting (target AUC 0.82) + Deep Learning (target AUC 0.87) — Fairness-Aware ML: reweighting, adversarial debiasing, demographic calibration — Explainable AI: SHAP values, LIME explanations for each recommendation • Define training data requirements and synthetic data generation plan • Create Figma wireframes: student onboarding, profile builder, recommendation feed with match rationale, application tracker • Create Figma wireframes: admin portal — program management, applicant review, enrollment analytics dashboard • Conduct prototype usability pre-test with 5 students | ML pipeline architecture doc · Model selection rationale · Training data schema · Fairness framework document · Figma wireframe prototype (student + admin flows) · Pre-test usability report (5 participants) · Feature engineering spec | ✅ Complete | Phase 2 | ML Lead / UX Lead
Wk 6 | Wk 6 – Sprint 1: Backend Foundation & Auth | Mar 02, 2026 | Mar 08, 2026 | • Implement user authentication: OAuth 2.0 (Google, ORCID), JWT token management, role-based access control (Student, Admin, SuperAdmin) • Build StudentProfile API: academic background (GPA, GRE, TOEFL), research interests (free text + taxonomy), publications list, SOP draft storage • Build InstitutionProfile API: program listings, faculty research areas, admission criteria, funding details • Deploy PostgreSQL schema (from Week 4 ER diagram) to AWS RDS • Configure Redis cache for session management and recommendation caching • Set up CI/CD pipeline: GitHub Actions → lint → unit tests → build → deploy to dev/staging • Implement end-to-end encryption (AES-256 at rest, TLS 1.3 in transit) | Auth service (OAuth2 + JWT) ✓ · StudentProfile CRUD API ✓ · InstitutionProfile CRUD API ✓ · PostgreSQL schema deployed ✓ · Redis configured ✓ · CI/CD pipeline live (GitHub Actions) ✓ · Encryption implemented ✓ · API documentation (Swagger UI) ✓ | ✅ Complete | Phase 3 | Backend Team
Wk 7 | Wk 7 – Sprint 2: ML Matching Engine Core | Mar 09, 2026 | Mar 15, 2026 | • Implement Collaborative Filtering module: — Matrix Factorization (SVD) on student-program interaction matrix — Neural Collaborative Filtering (NCF) with embedding layers • Build BERT/SciBERT NLP pipeline: — Generate embeddings for student research interest statements — Generate embeddings for program/faculty research descriptions — Semantic similarity scoring (cosine similarity on embedding space) — TF-IDF + Word Vector fallback for sparse profiles • Expose /recommend endpoint: accepts student profile, returns ranked program list with match scores • Build offline evaluation framework: Precision@K, Recall@K, NDCG, AUC metrics • Run first offline evaluation on synthetic dataset; establish baseline metrics | Collaborative Filtering module (SVD + NCF) ✓ · BERT/SciBERT embedding pipeline ✓ · Semantic similarity scorer ✓ · /recommend API endpoint ✓ · Offline evaluation framework ✓ · Baseline metric report (Precision@10, AUC) · Training pipeline on AWS SageMaker | ✅ Complete | Phase 3 | ML Team
Wk 8 | Wk 8 – Sprint 3: GNN, Explainable AI & Student Frontend | Mar 16, 2026 | Mar 22, 2026 | • Implement Graph Neural Network (GNN) layer: - Build student-program-faculty tripartite graph - Train GNN to capture higher-order relationships (advisor matches, lab culture fit) - Integrate GNN scores into hybrid recommendation ensemble • Build Explainable AI module: - SHAP values for feature attribution on each recommendation - LIME local explanations for individual predictions - Natural language explanation generator: 'This program matches because your research interests in [X] align with Prof. [Y]'s lab focus' • Implement Admissions Prediction model (Gradient Boosting + Deep Learning ensemble) • Build student-facing web app (React): - Onboarding flow (profile builder, interest taxonomy selector) - Recommendation feed with AI match scores + full rationale - Program detail pages with faculty profiles, funding info, deadlines - Serendipity toggle: discover programs outside predicted optimal set | GNN module integrated into ensemble ✓ · Explainable AI module (SHAP + LIME + NL explanations) ✓ · Admissions prediction model (AUC baseline) ✓ · Student web app v1 (onboarding + recommendations + program pages) ✓ · Serendipity feature ✓ · Internal UX review completed | ✅ Complete | Phase 3 | ML Team / Frontend
Wk 9 | Wk 9 – Sprint 4: Admin Portal, Analytics & Mobile | Mar 23, 2026 | Mar 29, 2026 | • Build University Admin Portal (React): — Program listing management (CRUD, requirements, deadlines, funding details) — Applicant review queue with AI-surfaced candidate profiles — Bidirectional messaging system (institution ↔ student) — Enrollment analytics dashboard: applicant trends, yield predictions, diversity metrics — Matching criteria configuration: institutions set their own weights • Build bidirectional notification engine: — Email notifications (SendGrid): application status, new messages, deadlines — Push notifications (Firebase FCM): mobile alerts — In-app notification center • Build mobile app beta (React Native): student flows — profile, recommendations, applications, messages • Open API integration endpoints for third-party systems | University admin portal v1 (program mgmt + applicant review + analytics) ✓ · Messaging system ✓ · Notification engine (email + push) ✓ · Mobile app beta (iOS + Android) ✓ · Open API endpoints documented ✓ · End-to-end smoke test across full user journey ✓ | ✅ Complete | Phase 3 | Full-Stack Team
Wk 10 | Wk 10 – Unit, Integration & Performance Testing | Mar 30, 2026 | Apr 05, 2026 | • Execute full unit test suite across all modules (target ≥80% coverage) • Run integration tests: auth → profile → recommendation → application → notification full pipeline • API contract testing (Pact): ensure consumer-provider compatibility • Load testing (k6/Locust): simulate 1,000 concurrent users; verify <2s API response • Security penetration testing: OWASP Top 10, SQL injection, XSS, CSRF, JWT vulnerabilities • Conduct first algorithmic bias scan: check recommendation output distributions across gender, race/ethnicity, institution type, first-gen status • Bug triage and priority fix sprint (P0/P1 bugs must be resolved before Phase 5) | Unit test report (≥80% coverage) · Integration test report · Load test results (1K concurrent users) · Security scan report (OWASP) · Bug tracker (P0/P1/P2 categorized) · First bias scan results by demographic group · Performance baseline dashboard | ✅ Complete | Phase 4 | QA Lead
Wk 11 | Wk 11 – ML Evaluation & Fairness Audit | Apr 06, 2026 | Apr 12, 2026 | • Run full ML evaluation on held-out test set: — Recommendation: Precision@10 (target ≥75%), Recall@10, NDCG, MRR — Admissions Prediction: AUC (Gradient Boosting target 0.82, Deep Learning target 0.87) — Diversity: Intra-list diversity, serendipity score • Conduct formal algorithmic fairness audit: — Demographic parity: recommendation rates by gender, race, SES, first-gen status — Equalized odds across groups — Apply adversarial debiasing and fairness reweighting if needed — Run 'serendipity' mechanism to surface under-represented programs • Conduct institutional matching audit: verify bilateral weights are being respected • Generate Explainable AI validation report: verify SHAP explanations are accurate and interpretable • Document all model cards (model architecture, training data, eval metrics, known limitations) | ML evaluation report (Precision@10, AUC, NDCG, diversity metrics) · Fairness audit report (demographic parity by group) · Adversarial debiasing results · Model cards (all models) · Explainable AI validation report · Recommendation quality dashboard · Bias mitigation changelog | ✅ Complete | Phase 4 | ML Lead / Ethics
Wk 12 | Wk 12 – UAT, Accessibility & Compliance | Apr 13, 2026 | Apr 19, 2026 | • Conduct think-aloud usability sessions with 10+ representative students (incl. first-gen, international, under-resourced) • Measure System Usability Scale (SUS) scores (target ≥4.0/5.0 = ≥80/100) • Conduct think-aloud sessions with 3 institution admin users • Run WCAG 2.1 AA audit: automated (axe-core) + manual screen reader testing (NVDA, VoiceOver) • Verify multilingual support (Arabic, Mandarin, Spanish) for international applicants • FERPA compliance review: data retention policies, student data access rights, consent flows • GDPR compliance review: purpose limitation, right to deletion, data portability, DPA agreements with partner institutions • Final P0/P1 bug resolution; performance regression checks • Stakeholder sign-off meeting: research team, legal, partner institutions | Usability test report (10+ participants, SUS scores) · WCAG 2.1 AA audit report · Multilingual support verification · FERPA compliance certificate · GDPR compliance certificate · DPA agreements with pilot institutions · Final bug-free release candidate · Stakeholder go/no-go sign-off ✓ | ✅ Complete | Phase 4 | UX Lead / Legal
Wk 13 | Wk 13 – Pilot Deployment & Institution Onboarding | Apr 20, 2026 | Apr 26, 2026 | • Deploy GradMatch to production (AWS ECS, multi-AZ, auto-scaling) • Set up CloudWatch monitoring, Datadog APM, PagerDuty alerting • Onboard 3 partner institutions: admin account setup, program data ingestion, API integration testing • Run 3-hour admin training workshops per institution (portal walkthrough, analytics dashboard, communication features) • Distribute pre-pilot surveys to participating students (baseline: current search methods, advising access, anxiety levels) • Configure 5-year cohort tracking framework (enrollment, GPA, completion, career outcomes) • Activate real-time recommendation serving and admissions prediction for pilot cohort • Hotfix protocol in place: 4-hour SLA for P0 issues | Production deployment ✓ · 3 partner institutions onboarded ✓ · Admin training completed (3 × workshops) ✓ · Pre-pilot surveys distributed ✓ · Cohort tracking framework active ✓ · Monitoring dashboards live ✓ · Hotfix protocol documented ✓ · Go-live announcement to pilot students ✓ | ✅ Complete | Phase 5 | DevOps / BD Lead
Wk 14 | Wk 14 – Pilot Monitoring, Feedback & Future Roadmap | Apr 27, 2026 | May 03, 2026 | • Monitor platform performance: uptime (target ≥99.5%), API response times, error rates • Track pilot engagement: daily active users, recommendations clicked, applications submitted, messages sent • Collect post-pilot surveys: student satisfaction, perceived recommendation quality, trust in AI explanations • Collect institution feedback: applicant quality, portal usability, analytics usefulness • Synthesize all feedback into actionable improvement backlog • Present pilot findings to research team and stakeholders • Draft Phase 6 roadmap: — Federated learning across institutions (privacy-preserving ML) — Reinforcement learning for recommendation sequence optimization — LLM-powered personal statement coaching (GPT-4 / Claude integration) — Cross-cultural matching adaptation for international programs — Expansion to 20+ institutions • Submit conference paper draft (ACM RecSys / AIED / EDM) | Pilot performance report (uptime, engagement, errors) · Post-pilot student survey results · Institution feedback synthesis · Improvement backlog (Phase 6) · Phase 6 roadmap document · Conference paper draft submitted · 5-year tracking protocol finalized · Final project report to stakeholders | ✅ Complete | Phase 5 | Research / PM

## 🤖 ML & Tech Stack
GRADMATCH — ML PIPELINE & TECHNOLOGY STACK DEEP DIVE
Matching Engine · NLP · Admissions Prediction · Fairness-Aware ML · Infrastructure
🧠 MATCHING ENGINE COMPONENTS
| Component | Algorithm / Model | Purpose & Details | Week Implemented | Performance Target | Library / Tool
🔷 | Collaborative Filtering — Matrix Factorization | SVD / ALS (Alternating Least Squares) | Decomposes student-program interaction matrix to identify latent factors. Captures patterns from students with similar profiles who applied to/succeeded in specific programs. Handles cold-start via content-based fallback. | Week 7 | NDCG@10 ≥ 0.72 | Surprise / implicit
🔷 | Collaborative Filtering — Neural | Neural Collaborative Filtering (NCF) | Replaces dot product with MLP to model non-linear student-program interactions. Embedding layers for students and programs; concatenated and passed through deep layers. Outperforms pure MF on sparse interaction data. | Week 7 | AUC ≥ 0.82 | PyTorch
🔶 | Graph Neural Network (GNN) | Graph Attention Network (GAT) | Builds tripartite graph: Students — Programs — Faculty. Message passing captures higher-order relationships: student's research interests → faculty advisor → program culture. Identifies 'hidden gem' programs missed by CF alone. | Week 8 | Precision@10 ≥ 0.75 | PyTorch Geometric
🟢 | NLP — Semantic Embeddings | BERT / SciBERT (Sentence Transformers) | Generates 768-dim embeddings for student research interest statements and program/faculty descriptions. SciBERT pre-trained on scientific corpus for domain accuracy. Cosine similarity ranking. Handles multilingual inputs (mBERT). | Week 7 | Semantic Sim ≥ 0.78 | HuggingFace Transformers
🟢 | NLP — Keyword Matching | TF-IDF + Word2Vec | Fallback for sparse profiles or short text. TF-IDF weighted keyword overlap. Word2Vec for synonym handling (e.g., 'ML' = 'machine learning'). Ensemble blended with BERT scores (α=0.3 TF-IDF, β=0.7 BERT). | Week 7 | Recall@10 ≥ 0.68 | scikit-learn / gensim
🔴 | Admissions Prediction — Gradient Boosting | XGBoost / LightGBM | Predicts admission probability given student profile and program requirements. Features: GPA percentile, GRE scores, publications count, research experience years, SOP quality score, program selectivity. SHAP for feature importance. | Week 8 | AUC = 0.82 | XGBoost / LightGBM
🔴 | Admissions Prediction — Deep Learning | Multi-layer Perceptron (MLP) Ensemble | Deep neural network on same feature set as GBM. Ensemble of GBM + MLP achieves higher AUC. Fairness-constrained training: demographic parity regularization term in loss function. Calibrated probability outputs. | Week 8 | AUC = 0.87 | PyTorch + Fairlearn
⚪ | Explainable AI | SHAP + LIME + NL Generator | SHAP values attribute each recommendation factor (research match, advisor fit, GPA alignment, funding). LIME provides local linear explanation per recommendation. NL Generator converts scores to human sentences: 'Your quantum computing research aligns strongly with Prof. X's active NSF-funded lab.' | Week 8 | Explanation Accuracy ≥ 90% | SHAP / LIME / GPT-4 API
🟡 | Fairness-Aware ML | Adversarial Debiasing + Reweighting | Adversarial network trained simultaneously to prevent demographic signal leakage. Sample reweighting to equalize recommendation rates across gender, race/ethnicity, SES, first-gen status. Regular demographic parity audits. 'Serendipity' injection to surface under-represented programs. | Week 8–11 | Demographic Parity Δ ≤ 0.05 | Fairlearn / AI Fairness 360
🟣 | Hybrid Ensemble | Weighted Score Fusion | Final recommendation score = w1×CF_score + w2×GNN_score + w3×NLP_score + w4×Admission_prob. Weights learned via Bayesian optimization on validation set. Student-configurable: slider to emphasize research fit vs. admission chance vs. funding. | Week 8 | Precision@10 ≥ 0.75 | Optuna (Bayesian Opt)
🏗️ INFRASTRUCTURE & TECH STACK
| Layer | Component | Technology Choice | Rationale | Week | Owner
🖥️ | Presentation | Web Application | React 18 + TypeScript + Tailwind CSS | Component-based, TypeScript for type safety, Tailwind for rapid responsive design | Wk 6–9 | Frontend
📱 | Presentation | Mobile Application | React Native + Expo | Code sharing with web app (~70%), cross-platform iOS/Android, OTA updates | Wk 9 | Frontend
⚙️ | Application | API Server | FastAPI (Python) + Uvicorn | Async Python, auto-generates OpenAPI docs, native Pydantic validation, fastest Python framework | Wk 6 | Backend
🔐 | Application | Authentication | OAuth 2.0 (Google/ORCID) + JWT + RBAC | Industry standard, ORCID for academic identity, JWT stateless tokens, role-based access | Wk 6 | Backend
🤖 | Service | ML Serving | FastAPI ML microservice + AWS SageMaker | Separate ML service for independent scaling; SageMaker for model training and A/B testing | Wk 7 | ML Team
📧 | Service | Notifications | SendGrid (email) + Firebase FCM (push) | SendGrid transactional email reliability; Firebase cross-platform push notifications | Wk 9 | Backend
🗄️ | Data | Primary Database | PostgreSQL 15 (AWS RDS Multi-AZ) | ACID compliance for student/application data, Row-level security for FERPA, Multi-AZ for HA | Wk 4 | Backend
📄 | Data | Document Store | MongoDB Atlas | Flexible schema for program descriptions, research statements, unstructured faculty data | Wk 4 | Backend
⚡ | Data | Cache | Redis 7 (AWS ElastiCache) | Recommendation caching (TTL 1hr), session management, rate limiting, pub/sub for notifications | Wk 6 | Backend
☁️ | Infrastructure | Cloud Platform | AWS (ECS Fargate, RDS, S3, CloudFront, Route53) | ECS for containerized microservices auto-scaling; S3+CloudFront for static assets CDN | Wk 4 | DevOps
🔄 | Infrastructure | CI/CD Pipeline | GitHub Actions → Docker → AWS ECS | Automated: lint → test → build image → push ECR → deploy ECS; branch-based envs | Wk 6 | DevOps
📊 | Infrastructure | Monitoring | CloudWatch + Datadog APM + PagerDuty | Full observability: metrics, traces, logs; PagerDuty for on-call alerting | Wk 13 | DevOps

## ✨ Features & User Stories
GRADMATCH — FEATURES, USER STORIES & ACCEPTANCE CRITERIA
Student Experience · University Admin Portal · Cross-Platform Features · Research Features
| Feature Area | User Story | Acceptance Criteria | Priority | Sprint | Status
👤 | Student — Profile Builder | As a student, I want to build a comprehensive academic profile so the AI can match me accurately | • GPA, GRE/GMAT, TOEFL/IELTS input fields with validation • Research interest taxonomy selector (500+ tags, hierarchical) • Free-text research statement (NLP-analyzed) • Publications/conference papers list (DOI import) • Work/research experience timeline • Funding preference (fellowship, RA, TA, self-funded) • Location and program type preferences (PhD, Masters, MEng) | 🔴 MUST | Sprint 1 | ✅
🎯 | Student — AI Recommendations | As a student, I want to receive personalized ranked program recommendations based on my full profile | • Ranked list of top 20 programs with match percentage • Match breakdown: research fit, advisor alignment, admission probability, funding match • Natural language explanation for each recommendation • 'Serendipity' toggle to explore beyond top matches • Filter by: country, ranking tier, funding type, program length • Real-time reranking when profile is updated | 🔴 MUST | Sprint 2 | ✅
🔍 | Student — Explainable AI | As a student, I want to understand exactly WHY each program was recommended | • SHAP-based factor attribution chart per recommendation • Top 3 matching reasons shown in plain English • Faculty profile cards: advisor's current research, recent publications, lab size • 'What if' simulator: see how improving GRE or adding a publication changes rankings • Confidence score and data freshness indicator | 🔴 MUST | Sprint 3 | ✅
📋 | Student — Application Tracker | As a student, I want to track all my applications in one place with real-time status updates | • Application status pipeline: Draft → Submitted → Under Review → Decision • Deadline countdown timer with calendar export • Document checklist per program (SOP, LORs, transcripts) • Status change push notifications (mobile + email) • Export application summary as PDF | 🔴 MUST | Sprint 4 | ✅
💬 | Student — Faculty Connection | As a student, I want to connect with faculty and current students at my target programs | • Faculty profile pages with research interests, publications, lab openings • In-app message request to faculty (routed via institution admin) • Current student testimonials and Q&A section • Virtual office hours scheduler integration | 🟡 SHOULD | Sprint 4 | ✅
🏛️ | Admin — Program Management | As a program coordinator, I want to manage our program listing so qualified students can find us | • CRUD interface for program details, requirements, deadlines • Faculty profile management with research area tagging • Funding package details (stipend, tuition waiver, health insurance) • Program culture tags (research-intensive, industry-connected, collaborative) • Bulk import from existing systems (CSV/API) • Preview how listing appears to students | 🔴 MUST | Sprint 4 | ✅
👥 | Admin — Applicant Review | As an admissions officer, I want to review AI-surfaced applicant profiles efficiently | • AI-ranked applicant queue based on program fit • Student profile view with research interest alignment visualization • Shortlisting and note-taking functionality • Bulk messaging to shortlisted candidates • Filter by: GPA range, research area, nationality, funding need • Export applicant list to CSV/PDF | 🔴 MUST | Sprint 4 | ✅
📊 | Admin — Enrollment Analytics | As a department head, I want actionable insights on applicant trends and yield predictions | • Applicant funnel dashboard: inquiries → recommendations → applications → admissions → enrollments • Research interest heatmap: which faculty attract the most aligned students • Yield prediction model per admitted student • Diversity metrics dashboard (gender, nationality, first-gen status) • Year-over-year comparison charts • Exportable reports for departmental planning | 🟡 SHOULD | Sprint 4 | ✅
⚖️ | Admin — Matching Criteria Config | As a program, I want to configure how the AI weights different matching criteria for our program | • Slider controls: research fit weight, GPA weight, GRE weight, funding match weight • Minimum threshold settings (min GPA, min GRE, required publications) • Diversity promotion toggle: boost under-represented groups in recommendation pool • A/B test different criteria configurations • Changes take effect within 1 hour (via cache invalidation) | 🟡 SHOULD | Sprint 4 | ✅
🔬 | Research — Cohort Tracking | As a researcher, I want to track matched student outcomes for 5 years to validate platform impact | • Annual survey pipeline to enrolled students (Year 1–5) • Track: GPA, research productivity, advisor satisfaction, program completion, career outcome • Comparison: GradMatch-matched vs. non-matched control cohort • IRB-compliant data collection with full consent management • Privacy-preserving analytics (k-anonymity ≥10) | 🟡 SHOULD | Sprint 4 / Phase 5 | ✅
🌍 | Accessibility — Multilingual | As an international student, I want to use GradMatch in my native language | • Full UI translation: Arabic, Mandarin (Simplified), Spanish, French, Hindi • RTL layout support for Arabic • Multilingual research interest taxonomy • mBERT for non-English research statements • Currency and date format localization | 🟡 SHOULD | Sprint 3 | ✅
🔗 | Platform — Open API | As a third-party developer or institution, I want to integrate GradMatch data with my systems | • RESTful API with OpenAPI 3.0 documentation • OAuth 2.0 machine-to-machine authentication • Webhook support for application status changes • Rate limiting: 1,000 requests/hour per institution • Sandbox environment for integration testing • API versioning (v1, v2 backward compatible) | 🟢 COULD | Sprint 4 | ✅

## 🔬 Research Methodology
GRADMATCH — RESEARCH METHODOLOGY & EVALUATION FRAMEWORK
Agile-Iterative Mixed-Methods · Quantitative ML Evaluation · Qualitative Usability · Longitudinal Outcomes
📚 RESEARCH DESIGN
| Method | Phase | Details | Output | Week
📖 | Systematic Literature Review | Phase 1 | Search strategy across ACM DL, IEEE Xplore, Google Scholar, ERIC using PRISMA guidelines. Keywords: graduate admissions, recommender systems education, fairness ML, NLP academic matching. Inclusion: peer-reviewed, 2015–2026, English. Target: 50+ papers synthesized into thematic matrix: (1) ML matching systems, (2) graduate outcomes research, (3) fairness & bias, (4) explainable AI in education. | Literature matrix (50+ papers) · Thematic synthesis report · Research gap analysis · Bibliography (Zotero) | Wk 2
🎤 | Semi-Structured Student Interviews | Phase 1 | 30 participants recruited via university mailing lists. Purposive sampling: 10 domestic undergrad, 10 international students, 5 first-gen, 5 graduate school re-applicants. Topics: current search methods, pain points, advising access, information needs, AI trust attitudes. 60-min sessions, audio recorded, transcribed, NVivo coded using thematic analysis. | 30 interview transcripts · NVivo codebook · Thematic analysis report · 5 student archetypes/personas | Wk 2
🏛️ | Institution Focus Groups | Phase 1 | 10 institutions: 3 R1 research universities, 3 teaching-focused, 2 international, 2 HBCUs/MSIs. Participants: admissions directors, program coordinators, DGS (Directors of Graduate Studies). Topics: current recruitment challenges, desired applicant qualities, data sharing constraints, diversity goals. 90-min sessions, 4–6 participants each. | 10 focus group summaries · Institution persona matrix (3 types) · Data sharing requirements · Partnership interest level | Wk 2
📊 | ML Quantitative Evaluation | Phase 4 | Offline evaluation on held-out test set (80/10/10 train/val/test split). Metrics: Precision@K, Recall@K, NDCG@K (K=5,10,20), Mean Reciprocal Rank (MRR), AUC-ROC for admissions prediction. Baseline comparisons: random, popularity-based, CF-only, NLP-only, GNN-only vs. full hybrid ensemble. Statistical significance testing (paired t-test, p<0.05). | Evaluation report · Metric comparison table · Ablation study (component contribution) · Statistical significance tests | Wk 11
⚖️ | Algorithmic Fairness Audit | Phase 4 | Measure recommendation rate disparities across: gender (male/female/non-binary), race/ethnicity (6 groups), SES (Pell grant eligibility as proxy), first-gen status, undergraduate institution type. Metrics: demographic parity difference (target Δ≤0.05), equalized odds, counterfactual fairness. Apply mitigation: adversarial debiasing, fairness constraints in loss function, post-hoc calibration. | Fairness audit report · Demographic parity metrics by group · Mitigation effectiveness comparison · Bias audit methodology document | Wk 11
🖱️ | Usability Think-Aloud Testing | Phase 4 | 12 participants (stratified: domestic/international, first-gen/continuing-gen, PhD/Masters seekers). Tasks: complete profile → view recommendations → explore match rationale → submit mock application → check status. Concurrent think-aloud protocol, screen + audio recorded. Measures: task completion rate, time-on-task, error rate, SUS questionnaire (target ≥80/100), NASA-TLX cognitive load. | Usability test report · Task completion rates · SUS scores per participant · Heatmaps · Prioritized UX issue list | Wk 12
📈 | Longitudinal Pilot Study | Phase 5+ | Pre-post design with 3 partner institutions. Pre: student survey before using GradMatch (search methods, anxiety, advising access perception). Post (3-months): application outcomes, satisfaction, perceived match quality. Follow-up (Year 1, 3, 5): enrollment, GPA, degree completion, career outcomes. Comparison cohort: students at same institutions who did not use GradMatch. IRB approved, FERPA/GDPR compliant. | Pre-pilot baseline survey · Post-pilot satisfaction survey · 5-year cohort tracking protocol · Annual follow-up survey templates | Wk 13–14+
🎯 EVALUATION METRICS DASHBOARD
| Metric | Category | Target | Measurement Tool | Phase
📐 | Precision@10 | ML – Recommendation Quality | ≥ 0.75 | Offline eval on held-out test set | Phase 4
📐 | NDCG@10 | ML – Ranking Quality | ≥ 0.70 | Offline eval on held-out test set | Phase 4
📐 | AUC-ROC (Admissions Pred.) | ML – Classification Quality | ≥ 0.87 (DL), ≥ 0.82 (GBM) | sklearn roc_auc_score on test set | Phase 4
⚖️ | Demographic Parity Δ | Fairness | ≤ 0.05 across all groups | Fairlearn / AI Fairness 360 | Phase 4
⚖️ | Equalized Odds | Fairness | ≤ 0.05 TPR disparity | Fairlearn / AI Fairness 360 | Phase 4
😊 | System Usability Scale (SUS) | UX Quality | ≥ 80/100 (≥ 4.0/5.0) | SUS questionnaire (12 participants) | Phase 4
🖱️ | Task Completion Rate | UX Quality | ≥ 90% | Think-aloud sessions | Phase 4
♿ | WCAG 2.1 AA | Accessibility | 100% pass | axe-core + NVDA + VoiceOver | Phase 4
🔒 | FERPA Compliance | Legal | 100% audit pass | Legal review checklist | Phase 4
🔒 | GDPR Compliance | Legal | 100% audit pass | DPO review + OneTrust | Phase 4
⚡ | API Response Time (p95) | Performance | < 2 seconds | k6 load test (1,000 concurrent) | Phase 4
🚀 | System Uptime (Pilot) | Reliability | ≥ 99.5% | CloudWatch / Datadog SLA monitor | Phase 5
📝 | Unit Test Coverage | Code Quality | ≥ 80% | pytest-cov / GitHub Actions CI | Phase 4
🌍 | Multilingual Support | Accessibility | 5 languages functional | Manual QA + native speaker review | Phase 3
📈 | Student Satisfaction (Pilot) | Pilot Outcome | ≥ 4.0/5.0 on perceived match quality | Post-pilot survey (Likert scale) | Phase 5

## 📊 Gantt Chart
GRADMATCH — GANTT CHART · Jan 26, 2026 → May 03, 2026
Wk# | Task / Track | Wk1 Jan 26 | Wk2 Feb 02 | Wk3 Feb 09 | Wk4 Feb 16 | Wk5 Feb 23 | Wk6 Mar 02 | Wk7 Mar 09 | Wk8 Mar 16 | Wk9 Mar 23 | Wk10 Mar 30 | Wk11 Apr 06 | Wk12 Apr 13 | Wk13 Apr 20 | Wk14 Apr 27
── PHASE 1: REQUIREMENTS & RESEARCH ──────────────────
Wk1 | Project Kick-off · Team Setup · GitHub/Jira/Confluence · IRB Application | ▓
Wk2 | Stakeholder Interviews (30 students + 10 institutions) · Literature Review (50+ papers) · Competitive Analysis |  | ▓
── PHASE 2: SYSTEM & ML DESIGN ──────────────────────
Wk3 | Requirements Elicitation · User Stories (100+) · Use Case Diagrams · Data Dictionary · MVP Scoping |  |  | ▓
Wk4 | 5-Layer Architecture · ER Diagram · OpenAPI 3.0 Spec · AWS Infrastructure · FERPA/GDPR Data Architecture |  |  |  | ▓
Wk5 | ML Pipeline Design (GNN+BERT+NCF) · Fairness Framework · Figma Wireframes · UX Pre-test (5 students) |  |  |  |  | ▓
── PHASE 3: AGILE DEVELOPMENT (4 SPRINTS) ───────────
Wk6 | Sprint 1: Auth (OAuth2+JWT) · Student/Institution Profile APIs · PostgreSQL · Redis · CI/CD Pipeline | [5 empty] | ▓
Wk7 | Sprint 2: Collaborative Filtering (SVD+NCF) · BERT/SciBERT Embeddings · /recommend API · Offline Eval Baseline | [6 empty] | ▓
Wk8 | Sprint 3: GNN Layer · Explainable AI (SHAP+LIME) · Admissions Prediction (AUC 0.87) · Student Web App | [7 empty] | ▓
Wk9 | Sprint 4: University Admin Portal · Analytics Dashboard · Notification Engine · Mobile App Beta · Open API | [8 empty] | ▓
── PHASE 4: TESTING & VALIDATION ─────────────────────
Wk10 | Unit Tests (≥80%) · Integration Tests · Load Test (1K users) · OWASP Security Scan · First Bias Scan | [9 empty] | ▓
Wk11 | ML Eval: Precision@10≥75%, AUC≥0.87 · Fairness Audit (Demographic Parity Δ≤0.05) · Model Cards | [10 empty] | ▓
Wk12 | UAT Think-Alouds (12 participants, SUS≥80) · WCAG 2.1 AA · FERPA/GDPR Sign-off · Release Candidate | [11 empty] | ▓
── PHASE 5: PILOT DEPLOYMENT ─────────────────────────
Wk13 | Production Deployment · 3 Institution Onboarding · Admin Training · Pre-Pilot Surveys · Cohort Tracking Setup | [12 empty] | ▓
Wk14 | Pilot Monitoring (≥99.5% uptime) · Post-Pilot Surveys · Feedback Synthesis · Phase 6 Roadmap · Paper Draft | [13 empty] | ▓
── CROSS-CUTTING TRACKS ──────────────────────────────
— | CI/CD Pipeline & DevOps (GitHub Actions → AWS ECS) | [5 empty] | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓
— | Documentation: Confluence + API Docs + Model Cards | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓
— | Bi-weekly Stakeholder Status Reports |  | ▓ |  | ▓ |  | ▓ |  | ▓ |  | ▓ |  | ▓ |  | ▓
— | Ethics & Compliance Reviews (ongoing) |  |  | ▓ |  | ▓ |  | ▓ |  | ▓ |  | ▓ | ▓ | ▓ | ▓
— | Algorithmic Bias Monitoring (ongoing from Sprint 2) | [6 empty] | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓ | ▓

## ⚠️ Risk Register
GRADMATCH — RISK REGISTER & MITIGATION STRATEGIES
Covering: ML Technical Risks · Research Risks · Ethical/Legal Risks · Partnership Risks · Operational Risks
| Risk Description | Probability | Impact | Risk Level | Mitigation Strategy | Owner | Phase
🤖 | ML model fails to reach Precision@10 ≥75% or AUC ≥0.87 targets | Medium | High | 🔴 HIGH | Ensemble fallback: degrade gracefully to CF-only (AUC≈0.79 acceptable minimum). Additional training data via synthetic augmentation. Weekly model review from Week 7. Hyperparameter sweep with Optuna. Ablation study to isolate underperforming component. If GNN fails, revert to NCF+BERT ensemble. | ML Lead | Phase 3–4
⚖️ | Algorithmic bias detected in fairness audit (Demographic Parity Δ >0.05) | Medium | High | 🔴 HIGH | Fairness-aware ML built from Day 1 (adversarial debiasing, reweighting). Weekly bias scans from Sprint 2. If audit reveals bias: apply post-hoc calibration, increase diversity promotion weight, engage external fairness consultant. Document all mitigation steps for research paper. | ML Lead / Ethics | Phase 3–4
🏛️ | Insufficient partner institution sign-ups for pilot (<3 institutions) | Medium | High | 🔴 HIGH | Identify and approach 8 candidate institutions (2.5× buffer) by Week 1. Tiered partnership model: full integration vs. data-sharing only. Begin legal/DPA templates in Week 4. Offer free pilot + co-authorship on research paper as incentive. BD Lead dedicated to partnerships from Week 1. | BD Lead | All
📊 | Poor data quality from partner institutions (missing fields, format inconsistencies) | High | Medium | 🔴 HIGH | Define data schema and validation rules in Week 4. Build ETL pipeline with quality checks and error reporting. Synthetic data generation for missing fields (GAN-based). Dry-run data ingestion in Week 12. Partner data steward assigned at each institution. | Data Analyst | Phase 3–5
👥 | Low student interview participation (<30 completing full sessions) | Low | High | 🟡 MEDIUM | Pre-recruit 50 volunteers before Week 2 (buffer for attrition). $25 gift card incentive. Offer flexible scheduling (Zoom, async video). Backup: extend to online survey (n=200) if in-person shortfall. University research office partnership for recruitment. | Research Lead | Phase 1
🔒 | FERPA or GDPR compliance gap discovered during legal review | Low | High | 🟡 MEDIUM | Privacy-by-design architecture from Week 4. Legal advisor reviews every sprint. Compliance checklist in Definition of Done. Engage external privacy attorney for Week 12 audit. DPA templates prepared by Week 6. No PII stored beyond stated purpose. | Legal/Privacy | Phase 2–4
🏃 | Scope creep beyond 14-week timeline (feature requests from stakeholders) | High | Medium | 🟡 MEDIUM | MoSCoW prioritization enforced. Feature freeze after Week 5 sprint planning. Change request process: PM approval + impact assessment required. Weekly scope review in stand-ups. Phase 6 backlog for post-pilot features. Stakeholders sign scope agreement in Week 3. | Project Manager | All
👤 | Key team member departure (ML Lead, Tech Lead, or Research Lead) | Low | High | 🟡 MEDIUM | All decisions documented in Confluence within 24hr. Pair programming policy (no single point of knowledge). Cross-training: each role has a documented backup. ML models and experiments tracked in Weights & Biases. 2-week knowledge transfer protocol if departure occurs. | Project Manager | All
☁️ | Cloud infrastructure cost overrun (AWS spend exceeds budget) | Medium | Medium | 🟡 MEDIUM | AWS Cost Explorer monitoring with weekly alerts. Use Spot Instances for ML training (70% cost reduction). Reserved instances for production RDS. Auto-scaling with cost caps. Container rightsizing in Week 6. Budget review checkpoint at Week 9. | DevOps Lead | Phase 3–5
🌐 | Cybersecurity breach or data exposure during pilot | Low | Critical | 🔴 HIGH | OWASP Top 10 penetration test in Week 10. AWS WAF, VPC isolation, IAM least-privilege. End-to-end encryption (AES-256 + TLS 1.3). Incident response plan documented Week 12. Cyber insurance. Bug bounty program post-launch. Regular dependency vulnerability scans (Snyk). | DevOps / Legal | Phase 4–5
😐 | Low student engagement with pilot platform (DAU < threshold) | Low | Medium | 🟢 LOW | Co-design with students in Phase 1–2 to build for real needs. Intuitive onboarding (3-step setup). In-app tooltips and tutorial videos. Gamification: profile completion progress bar. Email drip campaign during pilot. Institution champions (grad student ambassadors) to drive adoption. | UX Lead / BD | Phase 5
🔁 | CI/CD pipeline failures blocking sprint delivery | Low | Medium | 🟢 LOW | Thorough pipeline testing in Week 6. Rollback procedures documented. Feature flags for safe incremental releases. Staging environment mirrors production. Weekly pipeline health review. On-call DevOps rotation during pilot. | DevOps Lead | Phase 3–5